## in
Task Name | Role | Due Date | Notes
Host kickoff meeting to align on video needs | Shari Arroyo-Brown | 2024-08-29
PTV shares draft interview questions | Shari Arroyo-Brown | 2024-08-30
Shari provides feedback on v1 interview questions | Shari Arroyo-Brown | 2024-09-03 | PTV shares draft interview questions
IIP: Micah gives feedback on v1 video interview questions | Micah Carr | 2024-09-06 | PTV shares draft interview questions
Shari sends PTV feedback on v1 interview questions | Shari Arroyo-Brown | 2024-09-06
PTV finalizes interview questions for v2 | Shari Arroyo-Brown | 2024-09-09
PTV shares draft call sheets for CEOs | Shari Arroyo-Brown | 2024-09-06
Review call sheets, edit, send to CEO Teams | Shari Arroyo-Brown | 2024-09-06
PTV scouting BMP office for production | Shari Arroyo-Brown | 2024-09-10
Host pre-Production/Creative Meeting w/ PTV | Shari Arroyo-Brown | 2024-09-10
Production for Grameen interview | Shari Arroyo-Brown | 2024-09-13
Production for PL interview | Shari Arroyo-Brown | 2024-09-13
Production for Compass interview | Shari Arroyo-Brown | 2024-09-13
PTV delivers v1 rough cut of Ignite Impact Video 1 | Shari Arroyo-Brown | 2024-09-20
Review and provide feedback of Ignite Impact v1 rough cut Video 1 | Shari Arroyo-Brown | 2024-09-25
Review and provide feedback of Ignite Impact v1 rough cut Video 1 | Micah Carr | 2024-09-25
Send II Teamlets heads up for Ignite Impact Video1 fine cut review | Shari Arroyo-Brown | 2024-09-26
Send II Leaders heads up for Ignite Impact Video1 fine cut review | Shari Arroyo-Brown | 2024-09-30
PTV delivers fine cut of Ignite Impact Video 1 (v2) | Shari Arroyo-Brown | 2024-09-30
Review and provide feedback on v2 Fine Cut Ignite Impact Video 1 | Shari Arroyo-Brown | 2024-10-02
Review and provide feedback of v2 Fine Cut Ignite Impact Video 1 | Micah Carr | 2024-10-02
Send II Investee heads up for Ignite Impact Video1 fine cut review | Shari Arroyo-Brown | 2024-10-02
Send fine cut Ignite Impact Video 1 link to II Teamlets | Shari Arroyo-Brown | 2024-10-03
Teamlets submit their feedback to PolicyLink video directly in Vimeo link | Ignite Impact Teamlets | 10/3/2024 - 10/4/2024 | Focus attn on substantive investee org info/red flags/concerns on narrative. Send feedback by mid-afternoon 10/4
Send fine cut Ignite Impact Policylink video to II Leaders | Shari Arroyo-Brown | 2024-10-04 | Send by mid-afternoon 10/4
Ignite Impact Leaders review PolicyLink video/share feedback in Vimeo link | Ignite Impact Leaders | 10/4/2024 - 10/7/2024 | Focus attn on substantive investee org info/red flags/concerns on narrative. Send feedback by EOD 10/7
Review Ignite Impact v2 Fine Cut feedback from Teamlets/Leaders (Video 1) | Micah Carr | 2024-10-07
Send fine cut Ignite Impact Video 1 link to II Investee Teams | Shari Arroyo-Brown | 2024-10-08 | Focus attn on substantive investee org info/red flags/concerns on narrative. Ask for review, feedback, edits in 1-day turnaround mid-afternoon Oct. 8; return Oct. 9 EOD
Clean up feedback comments on Ignite Impact Video 1 fine cut | Shari Arroyo-Brown | 2024-10-09
PTV delivers final cut Ignite Impact PolicyLink Video (v3) | Shari Arroyo-Brown | 2024-10-14
Review final cut (v3) Ignite Impact Video 1 | Shari Arroyo-Brown | 2024-10-15
Review final cut (v3) Ignite Impact Video 1 | Micah Carr | 2024-10-15
Send Ignite Impact Team + InvesteesPolicyLink Final Cut Video | Shari Arroyo-Brown | 2024-10-16
PTV delivers Ignite Impact Videos 2+3 rough cut (v1) | Shari Arroyo-Brown | 2024-10-21
Review and provide feedback of Ignite Impact v1 rough cut Video 2+3 | Shari Arroyo-Brown | 2024-10-29
Review and provide feedback of Ignite Impact v1 rough cut Video 2+3 | Micah Carr | 2024-10-29
Send Teamlets heads up for Ignite Impact Video2+3 (v2)fine cut review | Shari Arroyo-Brown | 2024-11-01
Send Leaders heads up for Video 2+3 fine cut (v2) review | Shari Arroyo-Brown | 2024-11-04
PTV delivers fine cut of Ignite Impact Video 2+3 (v2) | Shari Arroyo-Brown | 2024-11-04
Send Investee heads up for Video1 (v2) fine cut review | Shari Arroyo-Brown | 2024-11-05
Review and provide feedback of v2 fine cut Ignite Impact Video 2+3 | Shari Arroyo-Brown | 2024-11-05
Review and provide feedback of v2 Fine Cut Ignite Impact Video 2+3 | Micah Carr | 2024-11-05
Send fine cut Ignite Impact Video 2+3 (v2) link to Teamlets | Shari Arroyo-Brown | 2024-11-06 | Send Nov. 6 morning - 2-day turnaround
Teamlets submit their feedback to Compass + Grameen videos directly in Vimeo link | Ignite Impact Teamlets | 11/6/2024 - 11/7/2024 | Focus attn on substantive investee org info/red flags/concerns on narrative. Send feedback by Nov. 7 EOD
Send fine cut II Grameen + Compass(v2)Vimeo link to Leaders | Shari Arroyo-Brown | 2024-11-07 | Ask for review, feedback, edits in 1-day turnaround Nov. 8 EOD
Ignite Impact Leaders review Grameen + Compass video/share feedback in Vimeo link | Ignite Impact Leaders | 11/72024-11/8/2024 | Focus attn on substantive investee org info/red flags/concerns on narrative. Send feedback by EOD Nov. 8
Review Ignite Impact v2 Fine Cut feedback from Teamlets/Leaders (Video 2+3) | Micah Carr | 2024-11-10
Send fine cut Ignite Impact Video 2+3 link to Investee Teams | Shari Arroyo-Brown | 2024-11-11 | Focus attn on substantive investee org info/red flags/concerns on narrative. Ask for review, feedback, edits in 2-day turnaround morning Nov. 11; return Nov. 12 EOD
Clean up feedback comments on (v2)Ignite Impact Video 2+3 fine cut | Shari Arroyo-Brown | 2024-11-13
PTV delivers final v3 Ignite Impact Video 2_3 | Shari Arroyo-Brown | 2024-11-18
Review final cut (v3) Ignite Impact Video 2+3 | Shari Arroyo-Brown | 2024-11-19
Review final cut (v3) Ignite Impact Video 2+3 | Micah Carr | 2024-11-19
Send Ignite Impact Team + Investees Grameen + Compass Final Cut Videos | Shari Arroyo-Brown | 2024-11-20
PTV delivers raw files of Ignite Impact Videos 1,2,3 | Shari Arroyo-Brown | 2024-11-22